# Project Scope: AI Game Review Agent

Timeline: 5 Working Days

Status: Updated Proposal (v2.0)

## 1. Project Overview

We are building an AI-powered agent that continuously monitors the platform for unreviewed game submissions. Instead of waiting for a manual trigger, the AI automatically identifies new games, analyzes their metadata, and submits a review proposal with a clear recommendation and reasoning for the admin to evaluate.

### The Core Mandate

The AI provides recommendations and reasons only. It never approves or rejects a game independently; that authority remains exclusively with the human administrator.

## 2. Operational Workflow

The system follows a 6-step automated cycle:

- Submission: A new game is uploaded to the platform.

- Detection: The AI agent continuously scans the database for games with no existing review.

- Analysis & Verification: The AI reads the title, description, category, developer name, and configuration. It then uses search and fetch tools to cross-reference submitted data against external sources, running evaluation metrics to assess accuracy before forming a recommendation.

- Proposal: The AI submits a review including a recommendation (e.g., "Accept" or "Decline") and a justification (e.g., "Description lacks gameplay details").

- Admin Review: The administrator reviews the AI's proposal. If declined with feedback, the AI moves to step 6.

- Retry Loop: The AI revises its review based on the feedback and resubmits. This repeats up to 3 times.

## 3. Analysis Scope

| Will Analyze | Won't Analyze |
| --- | --- |
| Game Title | Thumbnail Images |
| Description | Game Screenshots |
| Category Fit | Any Uploaded Media/Files |
| Developer Name | Binary Assets |
| Game Configuration | Source Code |
| Submission Date |  |

## 4. Data Accuracy & Verification

To ensure submitted game information is trustworthy, the AI goes beyond reading metadata in isolation. It actively uses search and fetch tools to cross-reference key fields against publicly available data, and applies evaluation metrics to score each submission before producing a recommendation.

### How Verification Works

• Search Tools: The AI queries external sources to confirm whether a developer, studio, or game title exists and matches the submitted description.

• Fetch Tools: The AI retrieves relevant web pages or data sources to validate claims in the game's description — such as genre, platform, or publisher.

• Evaluation Metrics: Each submission is scored across multiple dimensions before a recommendation is produced. If data cannot be verified or scores fall below threshold, the AI flags the inconsistency in its reasoning and adjusts its recommendation accordingly.

### Evaluation Metrics

| Metric | What It Checks |
| --- | --- |
| Title Authenticity | Does the game title match known records or appear fabricated? |
| Developer Credibility | Is the developer name a real or recognisable entity? |
| Description Quality | Is the description sufficiently detailed and consistent with the category? |
| Category Accuracy | Does the described content align with the claimed genre/category? |
| Data Consistency | Are all submitted fields internally consistent with each other? |

## 5. Retry Logic at a Glance

| Attempt | Event | Result |
| --- | --- | --- |
| 1st Submission | AI analyzes game metadata. | AI submits initial review/recommendation. |
| 2nd Submission | Admin declines with feedback. | AI incorporates feedback and resubmits. |
| 3rd Submission | Admin declines again. | AI incorporates new feedback for a final revision. |
| Final Failure | 3rd decline occurs. | Game is flagged as "Needs Manual Review"; AI stops processing. |

## 6. Delivery Plan

### Day 1: AI Brain Setup

- Integration with OpenAI (GPT) or Anthropic (Claude) APIs.

- Setup of the toggle system for provider switching (no vendor lock-in).

### Day 2: Training & Review Personas

- Defining the "Reviewer" logic: what constitutes a good vs. bad submission.

- Structuring the output: Written recommendation, reason, and improvement suggestions.

Integration of search and fetch tools for cross-referencing submitted game data against external sources, and configuration of evaluation metrics to score submission accuracy before a recommendation is produced.

### Day 3: Auto-Trigger & Retry Logic

- Implementation of the continuous scanning mechanism to detect unreviewed games.

- Development of the 3-attempt feedback loop based on admin decline reasons.

### Day 4: Admin Dashboard Updates

- Visual distinction for AI-generated reviews (clear labelling).

- Dashboard view for AI reasoning, suggestions, and current retry count.

- Automatic flagging of games that exhaust all 3 retries.

### Day 5: Testing & Handover

- End-to-end testing of the auto-detection and retry cycles.

- Final documentation and team walkthrough.

## 7. Hours Estimation

The table below provides an estimated breakdown of hours per phase. These estimates are based on the defined scope and are intended to help track work against the client's monthly hour allocation.

| Phase | Estimated Hours |
| --- | --- |
| Day 1: AI Brain Setup | 6 hours |
| Day 2: Training, Review Personas & Verification Tools | 8 hours |
| Day 3: Auto-Trigger & Retry Logic | 7 hours |
| Day 4: Admin Dashboard Updates | 6 hours |
| Day 5: Testing & Handover | 6 hours |
| Total | ~33 hours |

Note: These estimates reflect the defined scope only. Any changes in requirements or additional integrations may affect the final hour count.

## 8. Key Deliverables

- Auto-Detection: Agent automatically picks up unreviewed games without manual action.

- Provider Flexibility: Support for both OpenAI and Claude.

- Feedback Loops: AI self-corrects based on human rejection notes (up to 3x).

- Fail-Safe Mechanism: Automatic flagging for manual attention after failed iterations.

- Dashboard Integration: Distinct UI for AI-generated recommendations.

Data Accuracy Verification: AI cross-references submitted game data using search and fetch tools, applying evaluation metrics before forming any recommendation.

## 9. Out of Scope (Current Phase)

- Reviewing visual assets (thumbnails, screenshots, videos).

- Remembering developer history or feedback across different game submissions.

- Direct communication between the AI and the game developers.

## 10. Open Question

Which AI provider would you like to use for the initial setup

OpenAI (ChatGPT) or Anthropic (Claude)?